## Project Tracker
MediAssist AI Capstone Project Tracker
Phase | Module | Description | Deliverables | Weight % | Status | Start Date | Target Date
1 | Requirements Understanding | Understand business problem, architecture, datasets, personas | Requirement understanding document | 5% | Done | 2026-06-11 | 2026-06-12
2 | Solution Architecture | Create architecture diagrams, agent workflow, deployment design | Architecture breakdown document | 5% | Done | 2026-06-11 | 2026-06-12
3 | Data Ingestion Pipeline | PDF parsing, image ingestion, chunking, metadata creation, embeddings | Working ingestion pipeline | 10% | Not Started
4 | Vector Database Setup | FAISS/ChromaDB indexing and storage | Indexed knowledge base | 5% | Not Started
5 | Enterprise RAG Pipeline | Semantic search, hybrid retrieval, citations, metadata filtering | Working RAG chatbot | 10% | Not Started
6 | MCP Server Development | Build MCP server, PostgreSQL connectors and tools | MCP Server with tools | 10% | Not Started
7 | MCP Agent Integration | Agent tool calling and PostgreSQL retrieval | Working structured retrieval | 5% | Not Started
8 | Multimodal AI | Prescription analysis, OCR, report extraction using BLIP/LLaVA | Vision processing module | 10% | Not Started
9 | Multi-Agent Orchestration | Planner, Retriever, MCP, Vision, Reasoning agents in LangGraph | LangGraph workflow | 15% | Not Started
10 | Reasoning & Response Generation | Context synthesis and grounded recommendations | Response generation module | 5% | Not Started
11 | Evaluation Framework | LLM-as-Judge, hallucination detection, retrieval evaluation | Evaluation dashboard | 10% | Not Started
12 | Frontend Development | Streamlit chat, uploads, history, dashboards | Working UI | 5% | Not Started
13 | Dockerization | Dockerfile, Docker Compose, container testing | Containerized solution | 2.5% | Not Started
14 | Azure Deployment | Deploy application to Azure Container Apps | Live deployment | 2.5% | Not Started
15 | Documentation & Demo | GitHub, technical docs, architecture docs, final demo | Final submission package | 5%

## Project Tracker - New
Phase | Module | Description | Task | Deliverables | Status | Start Date | Target Date
1 | Requirements Understanding | Understand business problem, architecture, datasets, personas | Analyze project requirements, identify stakeholders, define use cases, study available datasets, document functional and non-functional requirements, define user personas and workflows | Requirement understanding document | Done | 2026-06-11 | 2026-06-12
2 | Solution Architecture | Create architecture diagrams, agent workflow, deployment design | Design system architecture, agent workflow, data flow, and deployment structure | Architecture breakdown document | Done | 2026-06-11 | 2026-06-12
3 | Project Setup & Planning | Setup project structure, Git, VS Code environment | Create repository, virtual environment, architecture design | Project Structure, HLD | Done | 2026-06-13 | 2026-06-17
5 | Document Ingestion Pipeline | Load healthcare documents | PDF, DOCX, TXT ingestion | Document Loader Module | Done | 2026-06-13 | 2026-06-17
6 | Text Processing & Chunking | Prepare documents for embedding | Cleaning, chunking | Chunked Documents | Done | 2026-06-13 | 2026-06-17
7 | Embedding Pipeline | Generate vector embeddings | Embedding generation | Embedding Store | Done | 2026-06-13 | 2026-06-17
8 | Vector DB Comparison | Create a comparison document for vectordb selection and upload it on github: Indexing algo, Search (keyword search, vector search, hybrid search), data scale (<1 M vectors) | ChromaDB, Pinecone, weaviate, FAISS | Github link with updated docs | Done | 2026-06-17 | 2026-06-19
9 | Vector Database Setup | Create a document of vector db comparisonStore embeddings | FAISS indexing | Vector Database | Done | 2026-06-17 | 2026-06-19
10 | Enterprise RAG Pipeline | Implement semantic retrieval | Similarity search, citations | RAG Engine | Done | 2026-06-17 | 2026-06-19
11 | Streamlit Frontend | Build chatbot UI | Chat interface, file uploads | Streamlit App | Done | 2026-06-17 | 2026-06-19
12 | FastAPI Backend | Build backend APIs | Chat APIs, upload APIs | Backend Services | Done | 2026-06-17 | 2026-06-19
13 | MCP Tool Development | Create healthcare data tools | Patient, appointment, billing tools | MCP Tool Registry
14 | Planner Agent | Break complex queries into tasks | Task decomposition | Planner Agent
15 | Retriever Agent | Retrieve enterprise documents | Document retrieval | Retriever Agent
16 | MCP Agent | Query structured data | Tool calling | MCP Agent
17 | Multimodal Agent | Process images and reports | OCR and image understanding | Multimodal Agent
18 | Reasoning Agent | Generate final responses | LLM reasoning | Reasoning Agent
19 | Agent Orchestration | Connect all agents | LangGraph workflow | Agent Workflow
20 | File Upload APIs | Upload documents and images | Upload endpoints | Upload Service
21 | Dashboard Development | Display metrics and traces | Analytics dashboard | Dashboard
22 | Evaluation Framework | Evaluate RAG quality | Faithfulness, relevance checks | Evaluation Report
23 | Guardrails & Security | Secure AI workflows | PHI masking, prompt protection | Security Layer
23 | Observability & Logging | Monitor workflows | Tracing and logs | Monitoring Dashboard
24 | Unit Testing | Validate modules | Test development | Unit Test Report
25 | Integration Testing | Validate end-to-end workflows | System testing | Integration Report
26 | Performance Testing | Measure scalability | Load testing | Performance Report
27 | Dockerization | Containerize solution | Docker image creation | Docker Images
28 | Azure Deployment | Deploy solution to Azure | Container deployment | Live Application
29 | Documentation & Demo | Create documentation and final demo | User guide, architecture docs | Technical Documentation, Demo